## WBS
대분류 | 중분류 | 완료일 | 비고
개발환경 구축 | nodejs 설치 |  | https://nodejs.org/ko/ - node : v16.17.0 - npm : 9.6.6
| db 설치 |  | https://mariadb.org/ - 10.9.2 - root-pw : dev1234
vscode 설치
vscode에 GitLens 설치
initialize | Initial commit | 2024-01-02 | gitlab에 project 생성
| [init] Express application generator. | 2024-01-02 | express-generator를 통한 node project 생성 reference : https://expressjs.com/ko/starter/generator.html #> express --view=pug ME
| [init] Add WBS. | 2024-01-02
| [init] Set port number to 1140. | 2024-01-02
| [init] Vulnerabilities error fix. | 2024-01-02
| [init] Added node_modules directory in .gitignore file. | 2024-01-02
| [init] Added package-lock.json file in .gitignore file. | 2024-01-02
| [init] Added ~$WBS.xlsx file in .gitignore file. | 2024-01-02
| [init] Apply Bootstrap 5 Template. | 2024-01-09 | Reference : https://themes.getbootstrap.com/shop/?s=phoenix
| [init] Page Partization. |  | - Use Bootstrap 5 Templates. - Reference URL : https://bootstrapious.com/p/bootstrap-sidebar - Reference : https://startbootstrap.com/template/simple-sidebar - Reference : https://www.w3schools.com/bootstrap5/bootstrap_templates.php - Reference : https://github.com/ratracegrad/nodejs_ejs_boilerplate
[UI] Add Font Awesome JS.
[UI] Change icon from fa-align-justify to fa-ellipsis-vertical.
[UI] Add icon in topbar menu.
[Init] Add ajax util.
[Init] Add service for linux.
favicon | [favicon] Add serve-favicon package.
[favicon] Add favicon image.
[favicon] Apply favicon.
Set favicon.
[favicon] Error code fix. - error message : GET http://localhost:3000/assets/favicon.ico 404 (Not Found)
gitignore
[gitignore] Add csv directory.
[gitIgnore] Add data directory in .gitignore file.
[gitIgnore] Add public/upload/ directory in .gitignore file.
DB | [db] Add mysql package.
[db] Add sample query for DB 'lemclass'.
[db] Add DB test code with mysql package.
[db] Add DB connection library.
[db] Add sample query for table 'users'.
[db] Pooling connections.
[db] Set timezone to 'Asia/Seoul' when connect DB.
[test] Add query for table 'teleinfo'.
[db] Add mysql connection library.
[db] Change db name from 'common_was' to 'amtel_tele'.
package | [package] Add moment and mement-timezone package.
[package] Add multer package.
환경변수 | [Constants] Change backup directory path.
[Constants] Change string value to constants variables.
[Constants] Add library for constants.
[environment] Add dotenv package.
[environment] Add usage code of dotenv.
Cookie
session | [session] Add express-session package.
| [session] Add sample code for express-session. |  | Reference : https://www.npmjs.com/package/express-session
[session] Add express-mysql-session package.
[session] Add sample code for express-mysql-session.
Auth | [UI] Add pages for login and signup.
[UI] Change user id from name to email.
[Session&Auth] Add passport and passport-local package.
[Session&Auth] Local athentication by passport.
Role 관리 | [Role] Implementation of delete function.
[Role] Implementation of update function.
[Role] Add plugin of google jquery.
[Role] Add ajax library.
[Role] Implementation of create function.
[Role] Implementation of read function.
[Role] Add role info to the session.
[Role] Add stub page for management roles.
[Role] Add router for management roles.
[Role] Add menu for management roles.
[Role] Ignore insert query when DB initialize.
[Role] Add admin user when service start.
[Role] Implementation of member registration function.
[Role] Initialize table for 'roles' when service start.
[Role] Update sample query for table 'users'.
[Role] Add sample query for table 'roles'.
Users 관리 | [Users] Prevents deletion of the admin account from the user management page.
[Users] Prevents deletion of the admin account from the user management page.
[User] Prevents modification of the admin account from the user management page.
[Users] Modified so that it cannot be registered with an admin account.
[Users] Fixed the admin account not being displayed in the user list.
[Users] Implementation of delete function.
[Users] Implementation of update function.
[Users] Implementation of create function.
[Users] Implementation of read function.
[Users] Add stub page for management users.
[Users] Add router for management users.
[Users] Add menu for management users.
backup | [backup] Create backup directory, if not exist.
[backup] Add sample query for table 'backup'.
[backup] Add stub router for backup management.
[backup] Load router for backup management.
[backup] Implement backup api for create.
[backup] Implement backup api for read.
[backup] Implement backup api for restore.
| [backup] Implement backup api for delete. |  | -
| [backup] Add menu for backup management. |  | -
| [backup] Add page-get-api for backup management. |  | -
| [backup] Add stub page for backup management. |  | -
| [backup] Implement backup UI for read. |  | -
| [backup] Implement backup UI for create. |  | -
| [backup] Implement backup UI for restore. |  | -
| [backup] Implement backup UI for delete. |  | -
[backup] Remove edit action icon.
[backup] Initialize table for 'backup' when service start.
[MultiUser] Initialize DB.
[MultiUser] Implementation of password encryption function.
[MultiUser] Update sample query for password encryption.
[MultiUser] Implementation of login function.
[MultiUser] Implementation of member registration function.
[MultiUser] Add input field for confirm-password.
Logging | logging with morgan.
[logging] Add package for winston.
[logger] Add sample code for winston.
[logger] morgan log to winston.
[logger] Code refactoring.
- Add logger library for winston.
[logger] Add package for winston-daily-rotate-file.
[logger] Add sample code for winston-daily-rotate-file.
acctype | Add sample query for table 'acctype'.
Add stub route for acctype.
Add acctype router in app.
Implement create api acctype.
Implement read api acctype.
Implement update api acctype.
Implement delete api acctype.
Add stub page for acctype.
Add menu for acctype.
[package] Add bootstrap-colorpicker package.
Implement create UI for acctype.
Implement read UI for acctype.
Implement update UI for acctype.
Implement delete UI for acctype.
teleinfos | Add sample query for table 'teleinfos'.
Add stub route for teleinfos.
Add teleinfos router in app.
Implement create api teleinfos.
Implement read api teleinfos.
Implement update api teleinfos.
Implement delete api teleinfos.
Add stub page for teleinfos.
Add menu for teleinfos.
Implement create UI for teleinfos.
Implement read UI for teleinfos.
Implement update UI for teleinfos.
Implement delete UI for teleinfos.
Add Search UI.
Add Package for json-2-csv.
map | Add menu for map.
Add router for map.
Add map router in app.
Add page for map.
pages | [Pages] Add router for pages.
[Pages] Load pages router module in app.
word | [Word] Add menu for word management.
[Word] Add router for word management.
[Word] Add management page for word.
[Word] Load word router module in app.
[Word] Add sample query for table 'word'.
[Word] Implement word api for create.
[Word] Implement word api for read.
[Word] Implement word api for update.
[Word] Implement word api for delete.
[Word] Implement word UI for create.
[Word] Implement word UI for read.
[Word] Implement word UI for updtae.
[Word] Implement word UI for delete.
categories | [Categories] Add sample query for table 'categories'.
[Categories] Add stub router for categories management.
[Categories] Load router for categories management.
[Categories] Implement categories api for create.
[Categories] Implement categories api for read.
[Categories] Implement categories api for update.
[Categories] Implement categories api for delete.
[Categories] Add menu for categories management.
[Categories] Add page-get-api for categories management.
[Categories] Add stub page for categories management.
[Categories] Implement categories UI for read.
[Categories] Implement categories UI for create.
[Categories] Implement categories UI for updtae.
[Categories] Implement categories UI for delete.
lectures | [Lectures] Add sample query for table 'lectures'.
[Lectures] Add stub router for lectures management.
[Lectures] Load router for lectures management.
[Lectures] Implement lectures api for create.
[Lectures] Implement lectures api for read.
[Lectures] Implement lectures api for update.
[Lectures] Implement lectures api for delete.
[Lectures] Add menu for lectures management.
[Lectures] Add page-get-api for lectures management.
[Lectures] Add stub page for lectures management.
[Lectures] Implement lectures UI for read.
[Lectures] Implement lectures UI for create.
[Lectures] Implement lectures UI for updtae.
[Lectures] Implement lectures UI for delete.
quiz_radio | [quiz_radio] Add sample query for table 'quiz_radio'.
[quiz_radio] Add stub router for quiz_radio management.
[quiz_radio] Load router for quiz_radio management.
[quiz_radio] Implement quiz_radios api for create.
[quiz_radio] Implement quiz_radios api for read.
[quiz_radio] Implement quiz_radios api for update.
[quiz_radio] Implement quiz_radios api for delete.
[quiz_radio] Add menu for quiz_radio management.
[quiz_radio] Add page-get-api for quiz_radios management.
[quiz_radio] Add stub page for quiz_radios management.
[quiz_radio] Implement quiz_radios UI for read.
[quiz_radio] Implement quiz_radios UI for create.
[quiz_radio] Implement quiz_radios UI for updtae.
[quiz_radio] Implement quiz_radios UI for delete.
supply_box | [supply_box] Add sample query for table 'supply_box'.
[supply_box] Add stub router for supply_box management.
[supply_box] Load router for supply_box management.
[supply_box] Implement supply_boxs api for create.
[supply_box] Implement supply_boxs api for read.
[supply_box] Implement supply_boxs api for update.
[supply_box] Implement supply_boxs api for delete.
[supply_box] Add menu for supply_box management.
[supply_box] Add page-get-api for supply_boxs management.
[supply_box] Add stub page for supply_boxs management.
[supply_box] Implement supply_boxs UI for read.
[supply_box] Implement supply_boxs UI for create.
[supply_box] Implement supply_boxs UI for updtae.
[supply_box] Implement supply_boxs UI for delete.
quiz_collins_test | [quiz_collins_test] Add sample query for table 'quiz_collins_test'.
[quiz_collins_test] Add stub router for quiz_collins_test management.
[quiz_collins_test] Load router for quiz_collins_test management.
[quiz_collins_test] Implement quiz_collins_tests api for create.
[quiz_collins_test] Implement quiz_collins_tests api for read.
[quiz_collins_test] Implement quiz_collins_tests api for update.
[quiz_collins_test] Implement quiz_collins_tests api for delete.
[quiz_collins_test] Add menu for quiz_collins_test management.
[quiz_collins_test] Add page-get-api for quiz_collins_tests management.
[quiz_collins_test] Add stub page for quiz_collins_tests management.
[quiz_collins_test] Implement quiz_collins_tests UI for read.
[quiz_collins_test] Implement quiz_collins_tests UI for create.
[quiz_collins_test] Implement quiz_collins_tests UI for updtae.
[quiz_collins_test] Implement quiz_collins_tests UI for delete.
notification | [notification] Add sample query for table 'notification'.
[notification] Add stub router for notification management.
[notification] Load router for notification management.
[notification] Implement notifications api for create.
[notification] Implement notifications api for read.
[notification] Implement notifications api for update.
[notification] Implement notifications api for delete.
[notification] Add menu for notification management.
[notification] Add page-get-api for notifications management.
[notification] Add stub page for notifications management.
[notification] Implement notifications UI for read.
[notification] Implement notifications UI for create.
[notification] Implement notifications UI for updtae.
[notification] Implement notifications UI for delete.
alliance_member | [alliance_member] Add sample query for table 'alliance_member'.
[alliance_member] Add stub router for alliance_member management.
[alliance_member] Load router for alliance_member management.
[alliance_member] Implement alliance_members api for create.
[alliance_member] Implement alliance_members api for read.
[alliance_member] Implement alliance_members api for update.
[alliance_member] Implement alliance_members api for delete.
[alliance_member] Add menu for alliance_member management.
[alliance_member] Add page-get-api for alliance_members management.
[alliance_member] Add stub page for alliance_members management.
[alliance_member] Implement alliance_members UI for read.
[alliance_member] Implement alliance_members UI for create.
[alliance_member] Implement alliance_members UI for updtae.
[alliance_member] Implement alliance_members UI for delete.
class | [class] Add sample query for table 'class'.
[class] Add stub router for class management.
[class] Load router for class management.
[class] Implement classs api for create.
[class] Implement classs api for read.
[class] Implement classs api for update.
[class] Implement classs api for delete.
[class] Add menu for class management.
[class] Add page-get-api for classs management.
[class] Add stub page for classs management.
[class] Implement classs UI for read.
[class] Implement classs UI for create.
[class] Implement classs UI for updtae.
[class] Implement classs UI for delete.
federation | [federation] Add sample query for table 'federation'.
[federation] Add stub router for federation management.
[federation] Load router for federation management.
[federation] Implement federations api for create.
[federation] Implement federations api for read.
[federation] Implement federations api for update.
[federation] Implement federations api for delete.
[federation] Add menu for federation management.
[federation] Add page-get-api for federations management.
[federation] Add stub page for federations management.
[federation] Implement federations UI for read.
[federation] Implement federations UI for create.
[federation] Implement federations UI for updtae.
[federation] Implement federations UI for delete.
history | [history] Add sample query for table 'history'.
[history] Add stub router for history management.
[history] Load router for history management.
[history] Implement historys api for create.
[history] Implement historys api for read.
[history] Implement historys api for update.
[history] Implement historys api for delete.
[history] Add menu for history management.
[history] Add page-get-api for historys management.
[history] Add stub page for historys management.
[history] Implement historys UI for read.
[history] Implement historys UI for create.
[history] Implement historys UI for updtae.
[history] Implement historys UI for delete.
title | [title] Add sample query for table 'title'.
[title] Add stub router for title management.
[title] Load router for title management.
[title] Implement titles api for create.
[title] Implement titles api for read.
[title] Implement titles api for update.
[title] Implement titles api for delete.
[title] Add menu for title management.
[title] Add page-get-api for titles management.
[title] Add stub page for titles management.
[title] Implement titles UI for read.
[title] Implement titles UI for create.
[title] Implement titles UI for updtae.
[title] Implement titles UI for delete.
qna_game | [qna_game] Add sample query for table 'qna_game'.
[qna_game] Add stub router for qna_game management.
[qna_game] Load router for qna_game management.
[qna_game] Implement qna_games api for create.
[qna_game] Implement qna_games api for read.
[qna_game] Implement qna_games api for update.
[qna_game] Implement qna_games api for delete.
[qna_game] Add menu for qna_game management.
[qna_game] Add page-get-api for qna_games management.
[qna_game] Add stub page for qna_games management.
[qna_game] Implement qna_games UI for read.
[qna_game] Implement qna_games UI for create.
[qna_game] Implement qna_games UI for updtae.
[qna_game] Implement qna_games UI for delete.
mission | [mission] Add sample query for table 'mission'.
[mission] Add stub router for mission management.
[mission] Load router for mission management.
[mission] Implement missions api for create.
[mission] Implement missions api for read.
[mission] Implement missions api for update.
[mission] Implement missions api for delete.
[mission] Add menu for mission management.
[mission] Add page-get-api for missions management.
[mission] Add stub page for missions management.
[mission] Implement missions UI for read.
[mission] Implement missions UI for create.
[mission] Implement missions UI for updtae.
[mission] Implement missions UI for delete.
star_level | [star_level] Add sample query for table 'star_level'.
[star_level] Add stub router for star_level management.
[star_level] Load router for star_level management.
[star_level] Implement star_levels api for create.
[star_level] Implement star_levels api for read.
[star_level] Implement star_levels api for update.
[star_level] Implement star_levels api for delete.
[star_level] Add menu for star_level management.
[star_level] Add page-get-api for star_levels management.
[star_level] Add stub page for star_levels management.
[star_level] Implement star_levels UI for read.
[star_level] Implement star_levels UI for create.
[star_level] Implement star_levels UI for updtae.
[star_level] Implement star_levels UI for delete.
unit_type | [unit_type] Add sample query for table 'unit_type'.
[unit_type] Add stub router for unit_type management.
[unit_type] Load router for unit_type management.
[unit_type] Implement unit_type api for create.
[unit_type] Implement unit_type api for read.
[unit_type] Implement unit_type api for update.
[unit_type] Implement unit_type api for delete.
[unit_type] Add menu for unit_type management.
[unit_type] Add page-get-api for unit_type management.
[unit_type] Add stub page for unit_type management.
[unit_type] Implement unit_type UI for read.
[unit_type] Implement unit_type UI for create.
[unit_type] Implement unit_type UI for updtae.
[unit_type] Implement unit_type UI for delete.
hero | [hero] Add sample query for table 'hero'.
[hero] Add stub router for hero management.
[hero] Load router for hero management.
[hero] Implement hero api for create.
[hero] Implement hero api for read.
[hero] Implement hero api for update.
[hero] Implement hero api for delete.
[hero] Add menu for hero management.
[hero] Add page-get-api for hero management.
[hero] Add stub page for hero management.
[hero] Implement hero UI for read.
[hero] Implement hero UI for create.
[hero] Implement hero UI for updtae.
[hero] Implement hero UI for delete.
battle_style | [battle_style] Add sample query for table 'battle_style'.
[battle_style] Add stub router for battle_style management.
[battle_style] Load router for battle_style management.
[battle_style] Implement battle_style api for create.
[battle_style] Implement battle_style api for read.
[battle_style] Implement battle_style api for update.
[battle_style] Implement battle_style api for delete.
[battle_style] Add menu for battle_style management.
[battle_style] Add page-get-api for battle_style management.
[battle_style] Add stub page for battle_style management.
[battle_style] Implement battle_style UI for read.
[battle_style] Implement battle_style UI for create.
[battle_style] Implement battle_style UI for updtae.
[battle_style] Implement battle_style UI for delete.
resource_request | [resource_request] Add sample query for table 'resource_request'.
[resource_request] Add stub router for resource_request management.
[resource_request] Load router for resource_request management.
[resource_request] Implement resource_request api for create.
[resource_request] Implement resource_request api for read.
[resource_request] Implement resource_request api for update.
[resource_request] Implement resource_request api for delete.
[resource_request] Add menu for resource_request management.
[resource_request] Add page-get-api for resource_request management.
[resource_request] Add stub page for resource_request management.
[resource_request] Implement resource_request UI for create.
[resource_request] Implement resource_request UI for read.
[resource_request] Implement resource_request UI for updtae.
[resource_request] Implement resource_request UI for delete.
counter | [counter] Add sample query for table 'counter'.
[counter] Add stub router for counter management.
[counter] Load router for counter management.
[counter] Implement counter api for create.
[counter] Implement counter api for read.
[counter] Implement counter api for update.
[counter] Implement counter api for delete.
[counter] Add menu for counter management.
[counter] Add page-get-api for counter management.
[counter] Add stub page for counter management.
[counter] Implement counter UI for create.
[counter] Implement counter UI for read.
[counter] Implement counter UI for updtae.
[counter] Implement counter UI for delete.
building | [building] Add sample query for table 'building'.
[building] Add stub router for building management.
[building] Load router for building management.
[building] Implement building api for create.
[building] Implement building api for read.
[building] Implement building api for update.
[building] Implement building api for delete.
[building] Add menu for building management.
[building] Add page-get-api for building management.
[building] Add stub page for building management.
[building] Implement building UI for create.
[building] Implement building UI for read.
[building] Implement building UI for updtae.
[building] Implement building UI for delete.
error | [error] vulnerabilities fix. |  | 4 vulnerabilities (3 high, 1 critical) To address all issues (including breaking changes), run: npm audit fix --force Run `npm audit` for details. npm notice npm notice New major version of npm available! 9.6.6 -> 10.2.4 npm notice Changelog: https://github.com/npm/cli/releases/tag/v10.2.4 npm notice Run npm install -g npm@10.2.4 to update! npm notice

## 건물
감시탑 | Watch Tower
지휘센터 | Headquarters
슈터캠프 | Shooter Camp
용사캠프 | Fighter Camp
개조차량기지 | Vehicle Depot
기수캠프 | Rider Camp
대사관 | Alliance Hall
바이러스연구소 | Research Lab
농장 | Farm
벌목장 | Lumber Mill
병원 | Infirmary
강철수집소 | Steel Plant
주유소 | Gas Field
바이오랩 | Virology Lab
창고 | Warehouse
연구센터 | Research Center
방어공사 | Trap Factory
보급소 | Supply Depot
무역소 | Trading Post
무기고
전쟁로비
성벽

## Sheet2
Add "ALL" option in acc_types.
Add function for get teleInfos.
Request acc_types when imeis is getted.
Add function for clear map.
Remove markers and polylines when update map.
Add map menu.
remove map menu.
Google map integration.
Change route color from red to blue.
1. Default acc_type is "rapid acceleration".
2. Display polyline for "safe driving".
1. Set imei selector.
2. Set acc_type selector.
3. Add acc_type query when search.
1. Add IMEI selector.
2. Add acc_type selector.
3. Remove IMEI input.
1. Add get IMEI lists api.
2. Add get acc type lists api.
3. Add acc_type filter option of teleinfo.
[teles] Add "Delete All Teles" button.
[db] Change length of timestamp column 20 to 25.
[teles] Add gps info.
[UI] Responsive design for mobile.
[download] Apply download csv.
[download] Apply download csv.
[download] Apply download csv.
[UI] Index page style for mobile.
[style] Remove padding of container.
[UI] Remove footer.
[UI] Remove footer.
[teles] Add "Clear" button.
[teles] Add filter.
[tele] Add filter condition of GET method.
[teles] Set MAX limit to 1000.
[style] Apply bootstrap 4.5.2
[style] Remove left, right margin of body.
[statistics] Empty data exception handling.
[statistics] Add statistics of teleinfo.
[db] Change 'root' password.
[teles] Add view for 'teles'.
[teles] Add route for 'teles' view.
[teles] Add route for 'teles'.
[teles] Add teles menu.
[api] Add api router.

## Table
Category
id | name | description | create_date | update_date | delete_date
Lecture
id | name | description | category_id | create_date | update_date | delete_date

## 키위베리
이름 | 성급 | 군단스킬 | 강화
캐리 | 5 | 부대 | 2
이블린 | 5 | - | 2
매트 | 5 | 부대 | 1
톰 | 5 | 부대 | 1
콜린스 | 5 | 기수 | 1
발레리 | 5 | 용사 | 0
마레 | 5 | - | 1
오스틴 | 5 | 슈터 | 1
애덤스 | 5 | 기수 | 1
제임스 | 5 | 부대 | 0
니뮐러 | 4 | 슈터 | 3
일리아 | 4 | - | 2
아스카 | 4 | 부대 | 3
라이언 | 4 | 기수 | 1
안덕리 | 4 | - | 2
피크스 | 3 | - | 5

## 울집개는크롱
이름 | 성급 | 군단스킬 | 강화
캐리 | 5 | 부대 | 1
이블린 | 5 | - | 0
매트 | 5 | 부대 | 1
톰 | 5 | 부대 | 0
콜린스 | 5 | 기수
발레리 | 5 | 용사 | 1
마레 | 5 | - | 0
오스틴 | 5 | 슈터 | 1
애덤스 | 5 | 기수 | 0
제임스 | 5 | 부대
스칼렛 | 5 | - | 0
이딘 | 5 | - | 0
아스카 | 4 | 부대
니뮐러 | 4 | 슈터 | 3
일리아 | 4 | - | 1
라이언 | 4 | 기수 | 1
안덕리 | 4 | - | 2
레이븐 | 4 | 용사- | 1
피니스 | 4 | - | 1
니카 | 4 | 용사 | 1
채서윤 | 4 | 부대 | 1
클로드 | 4 | 슈터- | 0
피크스 | 3 | - | 5

## Sheet1
보급 | 키위베리
|  | 강철 | 82만
|  | 목재 | 840만
|  | 식량 | 370만

## Message
조직개편 | 안녕하세요. 맹원님들.. 저보다 더 능력 있으신 분들이 많은데 제가 리더가 되어 죄송합니다. 맹원님들이 즐겁게 게임을 할수 있도록 최선을 다 하겠습니다. 우선 그간 캡틴님의 고군분투에 저흰 편안히 게임을 즐길수 있었으나, 캡틴님은 맘 고생이 심했으니라 생각이 듭니다. 우선 캡틴님께 감사의 말씀을 드립니다. 이번에 저희 연맹이 더 발전할 수 있도록 운영 규칙을 개편할까 생각 중입니다. 이번주 주말까지 초안을 작성하여 공지 드리도록 하겠습니다. 내용 이해에 혼란이 없도록 간략화 하여 전달 드리겠습니다. 혹시 부족한 점이 있다면 지적 부탁 드립니다. 경고 : 과도한 게임은 우리의 몸과 마음을 피폐하게 합니다.~~ ^^
공지사항 | [공지-연맹규정] 1. 초기닉네임 변경. 한글 또는 영문명으로 변경(원할한 소통을 위함) 2. 피난소는 길드의 연맹보루 근처로 지정이전 할 것.(원할한 파티, 이벤트, 집결을 위함) 3. 국가 룰 준수 할 것.(NAP 규칙) 다른 길드지휘관 및 타일 등 타겟시 전쟁 후 길드원에 피해를 줄 수 있음.(길드원 보호) 4. 1일 1회 출석체크. 장시간 출책 불가시 계급5에게 알릴 것. 5. 위 사항 위반시 킥대상 ※ 연맹규정은 연맹원의 제안에 의해 수정 및 삭제 가능 합니다. [공지-승급/강등 규정] 계급5 : 임기 1년, 1회 연임 가능, 매년 1월 1일 계급4의 회의를 통해 선출 계급4 : 계급5 에 의해 임명 계급3 : 계급4 에 의해 임명 계급2 : 연맹룰 1,2 를 준수한자 계급1 : 연맹에 가입한 자. ※ 승급/강등 규정은 연맹원의 제안에 의해 수정 및 삭제 가능 합니다. [공지 - 조직구조 및 역할 규정] LEX 연맹은 하기 조직으로 구성 및 관리된다. - 전쟁신 : 추후 업데이트 예정. - 모집관 : 추후 업데이트 예정. - 장군 : 추후 업데이트 예정. - 외교관 : 추후 업데이트 예정. - 정보부 : 연맹 운영 관리를 위한 서비스 개발. ※ 조직구조 및 역할 규정은 연맹원의 제안에 의해 수정 및 삭제 가능 합니다. [공지 - 이벤트 운영관리 규정] - 추후 업데이트 예정 ※ 이벤트 운영관리 규정은 연맹원의 제안에 의해 수정 및 삭제 가능 합니다. [공지 - 오픈체팅방 정보] - 체팅방 명 : 퍼즐오브Z-Lex - 체팅방 참여 방법 : 카카오톡에서 체팅방 명으로 오픈체팅 검색하여 참여 가능 합니다. 가입이 어려운 경우 하기 전화번호로 메시지를 남겨 주시면 가입 링크를 공유 드리겠습니다. - 010-4642-9938 [공지 - 도우미 서비스 운영관리] - 추후 업데이트 예정. 원할한 소통, 단합 및 우정을 위해 올림. ※ 경고 : 과도한 게임은 우리의 몸과 마음을 피폐하게 합니다.~~ ^^
현재 조직의 일원들은 탄탄하지만, 다들 시작한지 얼마 되지 않아 약소한 상태입니다. top 산하로 합류된다니 든든합니다. 연맹명은 크게 중요하지 않습니다. 다만 저희가 top 산하로 합류시 연맹의 운영 관리는 현 top member 가 하게 되는지 확인 부탁 드립니다. 추가로 저희 연맹은 S665 및 TOP 연맹에 큰 힘이 될거라 자신 합니다. 현재는 저희 연맹의 기틀을 다 보여드리지는 못하지만, 간단히 저희 연맹의 개시글을 통해 저희가 얼마나 TOP에 조력할 수 있는 능력이 있는지 예측 가능 하리라 봅니다. 저희의 안전한 이전을 도와 주시면 TOP와 S665에 조력 하도록 하겠습니다. 감사합니다. ~~ ^^
top 산하로 합류시 연맹의 운영 관리는 현 top member 가 하게 되는 건가요?

## 계급
계급 | 직급
5 | 리더 | 총괄
4 | 대장, 부대장 | 산하 조직원 관리, 계급을 승급/강등 한다. 조직의 임무를 수행한다.
3 | 조직원 | 조직의 임무를 수행한다.
2 | 연맹원 | 닉네
1 | 손님

## 조직
조직명 | 조직임무
전쟁신 | - 계급4에 속한다. - 전쟁 차관을 지정
모집관
장군
외교관
정보부

## 이벤트
Title | Start Date | Type | Message
연맹시련 | 2023.09.11(월요일) 09:00 | 일상 이벤트
음향함정 | 2023.09.11(월요일) 22:00
정수쟁탈전 | 2023.09.13(수요일) 19:22 |  | [공지] 정수쟁탈전 09/15 21:00 09/15(금요일) 저녁 9시에 정수쟁탈전 이벤트가 있습니다. 많은 참여 부탁 드리며, 시간조정 원하시면 말씀해 주세요. 즐거운 시간 되세요~~ ^^

## 관직_계급
관직권한
| 전쟁신 | 모집관 | 장군 | 외교관
정수 쟁탈전 신청 | O | O | O | O
건설 부대 송환 | O |  | O
모집/신청 개방 |  | O |  | O
연맹 금고 보상 분배 |  | O |  | O
연맹 스킬 사용 권한 | O | O | O | O
연맹 기지 대항전 오픈 |  | O |  | O
풍선배치 | O | O | O | O
계급권한
| 5 | 4 | 3 | 2 | 1
연맹 선물 수령 | O | O | O | O | O
멤버 계급 증가/감소 | O | O | O
멤버 추방 | O | O
연맹 초대 | O | O
연맹 신청 관리 | O | O
연맹 공지 편집 | O | O
대외 공지 편집 | O | O
연맹 깃발 변경 | O
연맹 명칭 닉네임 변경 | O
주요 언어 선택 | O
모집/신청 개방 | O
리더 양도 | O
연맹 해산 | O
관직 임명 | O
리더 탄핵 |  | O | O | O | O
이전 초대 | O | O
연맹 메시지 제거 | O | O
연맹 우편 | O | O | O
집결 종료 | O
메시지 신고 | O | O | O | O
연맹 과학 연구 | O | O
연맹 기지 대항전 오픈 | O
연맹 상점 입고 | O | O
연맹 과학 추천 | O | O
연맹 금고 보상 분배 | O
연맹 건축물 배치 | O | O
연맹 건축물 회수 | O | O
건설 부대 송환 | O
좀비 침공 오픈 | O | O
실험 기지 및 대포 수비 팀장 변경 | O
정수 쟁탈전 신청 | O
연맹 총동원 퀘스트 삭제 | O | O
연맹 시련 이벤트 오픈 | O
연맹 파티 이벤트 오픈 | O | O
[음향 함정] 오픈 | O
풍선배치 | O
연맹 대난투 신청 | O
연맹 스킬 사용 권한 | O
수원지 리그 신청 | O
연맹 쟁탈 신청 | O | O

## Sheet3
황무지 이벤트는 개인별로 포인트를 모아서, 개인 보상과 나라별 순위 보상을 받게 됩니다.
포인트 종류는 다음과 같은 세가지가 있습니다.
1. 처치 포인트
- 타 서버의 병력을 사망시킴으로서 얻는 포인트로 실험기지, 포대, 지휘센터, 채집지 상관없이 적군을 죽이면 얻는 포인트입니다.
2. 사망 포인트
- 실험기지와 포대에서 자신의 병력이 죽음으로써 얻는 포인트로, 특이하게 황무지 이벤트 이후 주지사가 국가정령(스킬) 사용시 포인트에 해당하는 만큼의 병력을 300% 속도로 생산할 수 있습니다.
- 흔히 사망퀘스트라고 말하는 부분이 이 포인트를 얻는 행위입니다.
3. 주둔 포인트
- 실험기지와 포대를 점령(리더 및 증원자 모두)하는 시간에 따라 얻는 포인트입니다.
이 중 사망 포인트를 효율적으로 얻기위해 흔히 말하는 병원 작업을 하게 되는데요..
포대 전투 시 사망자가 나오면 아래 병원의 순서대로 병력이 병원에 들어갑니다.
1. 일반병원
- 보통 좀동을 돌고 나면 병사들이 누워 있는 곳입니다.
- 포대 전투시 사상자의 70%는 이곳에 부상병으로 들어오고 30%는 사망합니다.(증발)
- 사망하는 30%에 대해서는 사망 포인트가 주어집니다.
- 자원을 사용하여 치료하며, 가속으로 빠르게 치료할 수 있습니다.
2. 심층치료센터
- 병원에 심층치료센터라고 따로 있는 부분으로, 병원이 수용량을 넘어서게 되면 이곳으로 병력이 들어옵니다.
- 수용량은 병원 수용량과 동일합니다.
- 심층 단계부터는 사망으로 판정되어 들어오는 모든 병력의 사망포인트를 얻게됩니다. (심층 70% + 사망 30% 에 대한 모든 포인트 획득)
- 치료는 나노약제라는 것을 사용하는데, 시간이 지나면 자동으로 차오르며 일일퀘스트를 달성할떄도 나노약제가 생기게 됩니다.
- 자원이 들지 않으며, 다이아를 사용하여 빠르게 치료할 수 있습니다.
3. 연맹병원
- 심층치료까지 가득 차게 되면 이후 연맹병원으로 부상병이 오게 됩니다.
- 치료할때 연맹코인이 들며, 개인별로 5만명의 병력이 수용가능합니다.
- 연맹코인을 모으기가 힘들어서 연맹병원에 오게 하는 것은 지양하는 것이 좋아요.
- 이 곳까지 다 차게되면 이후 사상자는 모두 사망합니다.
다시 돌아와서 사망퀘에 대한 이야기를 하자면..
사망포인트를 얻기위한 일련의 행위를 보통 사망퀘라 칭하며, 이를 효율적으로 하기 위해 황무지 이벤트 전에 병원을 택시로만 가득 채웁니다.
이는 두가지 이유 때문인데요.
1. 택시는 치료비가 가장 쌉니다. (병원에서는 자원과 가속을 이용해서 치료해야 하므로..)
2. 병원을 가득 채워두면 이후 사상자는 모두 심층으로 가게 되는데, 그러면 사상자의 100%에 대해 포인트를 획득할 수 있습니다.
이러한 이유로 병원작(택시로 병원 채우기)을 한 뒤 사망퀘(상대 포대에다 병력을 사망시키기)를 진행합니다.
추가적으로 황무지 이벤트에는 각 서버별 대표자가 NAP 조약을 맺는 경우가 많은데요.
10T 5만
9T이하 무제한
영웅, 장비, 부품, 칩, 큐브, 신체기관 해제
등과 같은 조약을 걸어서 서로의 피해를 최소하 해요.
위 내용에 맞게 상대서버에 가서 대포에 자살(ㅜㅜ)을 시키면 됩니다.

## 역할
role
id | name | contents

## 연맹원
맹원명 | 조직 | 직위
타오스 | 총괄 | 리더
캡틴 | 총괄 | 참모
달님0913 | 장군 | 대장
키위베리 | 모집관 | 대장
호두바라기 | 전쟁신 | 대장 | 호빵맨, 호두마미
호롤롤로루 | 외교관 | 대장
KICET-RIKEN | 전쟁신 | 부대장
Mydogcrong | 장군 | 부대장
사랑비 | 외교관 | 부대장
수동조작 | 모집관 | 부대장
술취한홍구 | 장군 | 부대원
좀비잡는어부 | 장군 | 부대원
지금아니면 | 장군 | 부대원
파고다야 | 모집관 | 부대원
YOOHOO | 모집관 | 부대원
구리구리힝구리 | 모집관 | 부대원
코나니 | 전쟁신 | 부대원
핀슨장 | 전쟁신 | 부대원
백마탄공주님 | 전쟁신 | 부대원
시랑소랑 | 외교관 | 부대원
양봉이음붕이 | 외교관 | 부대원
카마빙가

## 영웅
name(KOR) | name(ENG) | 성급 | 병과 | 스타일
오스틴 | ephraim | 5 | 슈터 | 냉정 |  | 성급 | Star Level
마레 | mc_carty | 5 | 내정 | 충동 |  | 2* | 3* | 4* | 5* | 6* | 7*
캐리 | requiem | 5 | 슈터 | 충동
토모요 | tomoyo | 5 | 용사 | 열렬 |  | 병과 | Unit Type | img
이블린 | eve | 5 | 내정 | 열렬 | 1 | 용사 | Fighter
제임스 | mars | 5 | 슈터 | 용감 | 2 | 슈터 | Shooter
남하율 | nam_hayul | 5 | 슈터 | 용감 | 3 | 기수 | Rider
마르크 | mantis | 5 | 내정 | 신중 | 4 | 내정 | Economy
애덤스 | obsidian | 5 | 슈터 | 용감 | 5 | 개조차량 | Vehicle
콜린스 | fox | 5 | 기수 | 냉정
가호 | chia_hao | 5 | 내정 | 냉정 |  | battle_style_kr | battle_style_kr | img_path
발레리 | ulrik | 5 | 용사 | 용감 | 1 | 용감 | brave
매트 | marlowe | 5 | 기수 | 열렬 | 2 | 냉정 | calm
톰 | meyers | 5 | 용사 | 신중 | 3 | 열렬 | avid
사무엘 | samuel | 5 | 내정 | 용감 | 4 | 신중 | wary
앙헬 | angelo | 5 | 기수 | 용감 | 5 | 충동 | rash
나타샤 | nataly | 5 | 용사 | 용감
스칼렛 | scarlett | 5 | 내정 | 충동
사피아 | phoenix | 5 | 슈터 | 충동
레아 | leah | 5 | 내정 | 충동
델라 | dara | 5 | 슈터 | 충동
장기에프 | zephyr | 5 | 용사 | 냉정
안나 | levina | 5 | 기수 | 냉정
유즈루 이치로 | hanyu_ichiro | 5 | 용사 | 냉정
로데 | ironclaw | 5 | 내정 | 신중
에디 | lady_m | 5 | 내정 | 신중
이딘 | lee | 5 | 내정 | 신중
로라와 제시 | lora_and_jessie | 5 | 슈터 | 신중
무심 | wuxin | 5 | 내정 | 신중
에만다 | agent_x | 5 | 내정 | 열렬
아이리스 | atropos | 5 | 용사 | 열렬
월리 | wali | 5 | 기수 | 열렬
니뮐러 | hartwell | 4 | 슈터 | 용감
니카 | seo_yun | 4 | 용사 | 용감
일리아 | varvara | 4 | 내정 | 열렬
라이언 | reyn | 4 | 기수 | 충동
클로드 | griffin | 4 | 슈터 | 신중
채서윤 | chae_seoyun | 4 | 용사 | 냉정
피니스 | dr_j | 4 | 내정 | 열렬
안덕리 | otto | 4 | 내정 | 냉정
아스카 | devana | 4 | 용사 | 충동
루시우스 | dom | 4 | 기수 | 신중
레이븐 | sanguine | 4 | 용사 | 냉정
오멘스 | malcolm | 3 | 슈터 | 신중
젤스 | doc_gray | 3 | 기수 | 열렬
줄리아 | barbie | 3 | 용사 | 용감
바덴 | bard | 3 | 슈터 | 용감
하일라 | anahita | 3 | 내정 | 열렬
피크스 | flint | 3 | 내정 | 냉정
루키우스 | marshall | 3 | 내정 | 충동
레거 | percival | 3 | 기수 | 신중
예문 | chester | 3 | 내정 | 충동
요커스 | noct | 3 | 용사 | 냉정
진 | kento | 2 | 내정 | 신중
아이린 | amber | 2 | 슈터 | 충동
다라 | queenie | 2 | 용사 | 용감
자비우스 | xavis | 2 | 내정 | 열렬
헨리 | maverick | 2 | 기수 | 냉정
심보로 | sembello | 6 | 내정 | 용감
지니 | ginny | 6 | 내정 | 충동
한나 | hanna | 6 | 내정 | 냉정
에이미 | amelia | 6 | 내정 | 열렬

## 병과
병과 | Unit Type | img
용사 | Fighter
슈터 | Shooter
기수 | Rider
내정 | Economy
개조차량 | Vehicle

## 스타일
battle_style_kr | battle_style_kr | img_path
용감 | brave
냉정 | calm
열렬 | avid
신중 | wary
충동 | rash